Situation Report RIMPAC

Saturday 10 June

Operation Strong Angel

Operations

- Land CMOC established at both Capitol and field level

- Land Exercise Control (EXCON) established

- Points of contact for UN team and MNF on the ground established

- HCR at field and OCHA at HQ level have agreed to a daily meeting schedule

# General Update

Under UNHCR’s coordination the refugee camp should be fully operational by this evening. 2000 newly arrived refugees are currently in the camp. UNHCR field staff estimate that approximately 10,000 refugees have crossed over the border. However access to the border is still virtually impossible due to security concerns. There were military reports of continued shooting on the Orange side of the crossing.

HCR and WFP conducted preliminary food and health assessments in the camp today in preparation for the expected influx in the coming days. UNICEF conducted an assessment mission to the local hospital and clinics.

UNHCR and UNICEF requested assistance for water and health facilities to be available at the camp.

Logistics & Humanitarian Supplies

Two C130’s arrived today carrying food and non-food items for WFP, UNHCR and UNICEF.  Food items included 10mt of humanitarian daily rations (HDR’s) and 2 mt of High Protein Biscuits (HPB’s). Non food items included jerry cans, medical kits, ORS,cooking utensils, blankets and mattresses. A request was made to the military to unload, store and standby for delivery to the camp. It has been agreed that the Red Cross will be responsible for secondary distribution. WFP made a request for trucks incase there is a shortage of transport available.

# Operational Plan

UN emergency Operation Plan will be available tomorrow as a working document. The three phase plan includes: Phase 1:  First 48 hours, Phase 2:  Four to six weeks, Phase 3:  Handover

# Security

UN team was briefed today about potential for unexploded ordinances and mines in the area. There continue to be reports of shooting over the border.

# Telecommunications and Information Technology

- Computer LAN, laptop computers and email services are up and running.

- Satellite telephone installed

- Security Vehicle tracking procedures are now active monitoring movement of UN staff and vehicles outside of camp

- Extra handsets have been distributed to three military counterparts

- The VHF radio network has proven to be critical and effective

- One telephone landline will be established tonight

# UN Team Contact Number

Satellite phone  00874762088443

Peter Scott-Bowden  39 348 6027

Lionel Marre 39348 6099 441

Abby Spring 917 302 9325

Peter McDermott 917 378 6990

Philippe Duamelle 917 856 1571

Tanny Noorlander  917 378 6969

Peter Casier 32 478 471 883

Jo Hegenauer  no cell phone number