## Sheet1
ID | Road Desc | District(s) | Organization | Type | Length(km) | Start Lat | Start Long | End Lat | End Long | Design Complete | Start Date | End Date (Est) | Status | Subcontractor | Notes
1 | Jalalabad to Chaparhar D.C | Jbad/Chaparhar | UNOPS | Paved | 12 |  |  |  |  | N | 2006-02-01 |  | Postponed
2 | Zamarkhel to Mourga | Pachir Wa Agam | RAMP | Compacted Gravel | 2 |  |  |  |  | Y |  |  | ?
3 | Pachir DC to Mir Afzali Ziarat | Pachir Wa Agam | RAMP | Compacted Gravel | 6.4 |  |  |  |  | Y |  |  | ?
4 | Pachir DC to Girri Khil | Pachir Wa Agam | RAMP | Compacted Gravel | 12.3 |  |  |  |  | Y |  |  | ?
5 | Pachir DC to Bama Khil | Pachir Wa Agam | RAMP | Compacted Gravel | 3.15 |  |  |  |  | Y |  |  | ?
6 | Gullaee Road (Siachow) | Ghanikhel/Shinwar | RAMP | Compacted Gravel | 9.1 |  |  |  |  | Y |  |  | ?
7 | Ghrabawa to Anbar Khana | Ghanikhel/Shinwar | RAMP | Compacted Gravel | 8.4 |  |  |  |  | Y |  |  | ?
8 | Nahr-e-Shahi to Khushgunbad | Behsood | RAMP | Compacted Gravel | 9.3 |  |  |  |  | Y |  |  | ?
9 | Kaja-Wazir to Molavi Saib Ziarat | Khogyani | RAMP | Compacted Gravel | 3.9 |  |  |  |  | Y |  |  | ?
10 | Sra Qala to Qailaghou | Khogyani | RAMP | Compacted Gravel | 3.25 |  |  |  |  | Y |  |  | ?
11 | Wazir Dosaraka to Karam Khil | Khogyani | RAMP | Compacted Gravel | 1.8 |  |  |  |  | Y |  |  | ?
12 | Hadira(Cemetery) to Shikhanou | Khogyani | RAMP | Compacted Gravel | 3.35 |  |  |  |  | Y |  |  | ?
13 | Akram Khel to Mourgha | Sherzad | RAMP | Compacted Gravel | 9 |  |  |  |  | Y |  |  | ?
14 | Khot Test Road | Khot | RAMP | Compacted Gravel | 5 |  |  |  |  | Y |  |  | Complete | Afghan AID
15 | Kama to Goshta Test Road | Kama/Goshta | RAMP | Compacted Gravel | 10 |  |  |  |  | Y |  |  | Complete | RI
16 | Kama to Goshta (Remaining) | Kama/Goshta | RAMP | Compacted Gravel | 10 |  |  |  |  | Y |  |  | WIP | DADF
17 | Landa Booch | Kama | RAMP | Compacted Gravel | 10.45 |  |  |  |  | Y |  |  | WIP | DADF
18 | Qalay Akhond to Sangar Saray | Kama | RAMP | Compacted Gravel | 6.45 |  |  |  |  | Y | 2005-07-01 |  | WIP | HADF
19 | Zarshoy | Kama | RAMP | Compacted Gravel | 5.45 |  |  |  |  | Y |  |  | WIP | DADF
20 | Arbaban | Kama | RAMP | Compacted Gravel | 1.95 |  |  |  |  | Y | 2005-08-01 |  | WIP | HADF
21 | Shirger Road | Kama | RAMP | Compacted Gravel | 13 |  |  |  |  | Y |  |  | ?
22 | Pewi Kandow to Tangi | Deh Bala | NEEP/MoPW | Compacted Gravel | 20.9 | 70.4629 | 34.166 | 70.4737 | 34.0742 | Y | 13..January 2005 | 31.Oct.2005 | Completed
23 | Shir Zad to Dosaraka Wazir Tangi | Khogyani | NEEP/MoPW | Compacted Gravel | 18.9 | 70.194 | 34.3499 | 70.1686 | 34.2015 | Y | 4.May.2005 | 15.feb.2006 | Completed
24 | Joe Sar to Melawi Kandow | Nazyan | NEEP/MoPW | Compacted Gravel | 11.1 | 70.8089 | 34.2111 | 70.8099 | 34.1271 | Y | 25.April.2005 | 30.March.2006 | 90% completed
25 | Ghani Khel to Nazyan | Ghanikhel/Nazyan | NEEP/MoPW | Compacted Gravel | 9.4 | 70.8089 | 3421109 | 70.8099 | 34.1271 | Y | 25.Sep.2005 | 22.Feb.2006 | Completed
26 | Dand to Bawli (DBST) | Surkh Rod | NEEP/MoPW | DBST | 4.5 | 70.3104 | 34.4114 | 70.2738 | 34.3917 | Y | 01.Oct.2005 | 31.May.2006 | on going
27 | Ghani Khel to Achin | Achin | NEEP/MoPW | Compacted Gravel | 10 |  |  |  |  | Y | 1.Dec.2005 | 30.April.2006 | on going
28 | Surkh Rod to Bar Khokheyl | Surkh Rod | DAI (ALP) | Cobblestone | 11 |  |  |  |  | Y |  |  | ?
29 | Goshta to Lal Pur DC | Goshta/Lal Pur | DAI (ALP) | Cobblestone | 25 |  |  |  |  | N |  |  | Not Funded
30 | Surkh Road to Khogyani DC | Surkh Rod/Khogyani | DAI (ALP) | Paved | 13 |  |  |  |  | N |  |  | Proposed |  | 13km from end of pavement in Surkh Rod to Khogyani. Design only in 2006. Only 5km asphalt in 2006.
31 | HW1 to Goshta Bridge | Bati Kot | DAI (ALP) | Cobblestone | 15 |  |  |  |  | N |  |  | Proposed
32 | Canal 29 | Shinwar | RAMP | Compacted Gravel | 5 |  |  |  |  | Y |  |  | ?
33 | Shewa to Dari Nur | Kuz Kunar/Dari Nur | CERP | Compacted Gravel | 8 | 36.2108 | 71.9597 | 35.8836 | 71.5736 | Y | 2006-02-01 | 2006-05-01 | WIP
34 | Chapahar to Pachir Wa Agam DC | Chaparhar/Pachir Wa Agam | CERP | Paved? | 13.6 |  |  |  |  | N |  |  | Denied Funding
35 | JAF Road | Jalalabad | CERP | Paved | 2.5 | 34.4138 | 70.4754 | 34.3998 | 70.4852 | Y | 2006-02-01 | 2006-05-01 | WIP
36 | Shinwar to Nazyan DC | Shinwar/Nazyan | NEEP/DoPW | Compacted Gravel | 15 |  |  |  |  | Y |  |  | WIP
37 | HWY1 to Shai Kot | Rodat | CERP | Compacted Gravel | 10 | 34.355 | 72.1289 | 35.8675 | 70.8122 | Y | 2006-02-01 | 2006-05-01 | WIP
38 | HWY135 to Sherzad DC | Sherzad | CERP | Cobblestone | 7.8 | 34.3936 | 71.1267 | 35.1128 | 70.1181 | N |  |  | Proposed (Spring 06)
39 | Tangi qasam abad | Behsud | DAI (AINP) | Compacted Gravel | ? | 34.5193 | 70.5467 | 34.4469 | 70.4598 | Y |  |  | WIP
40 | SHO QALAI,SOTAN | Dara I noor | DAI (AINP) | Compacted Gravel | ? | 34.6759 | 70.5957 | 34.7258 | 70.6393 | Y |  |  | WIP
41 | Chinar Kaly | Dur Baba | DAI (AINP) | Compacted Gravel | ? | 34.091 | 70.9819 | 34.1158 | 70.0036 | Y |  |  | WIP
42 | Woch khur | Hesarak | DAI (AINP) | Compacted Gravel | ? | 34.3112 | 69.7637 | 34.2924 | 69.8097 | Y |  |  | WIP
43 | Chartot | Hesarak | DAI (AINP) | Compacted Gravel | ? | 34.2707 | 69.7995 | 34.2924 | 69.8097 | Y |  |  | Completed
44 | CITY OF JALALABA | Jalalabad | DAI (AINP) | Compacted Gravel | ? | 34.4309 | 70.456 | 34.4279 | 70.4578 | Y |  |  | WIP
45 | Jalalabad City | Jalalabad | DAI (AINP) | Compacted Gravel | ? |  |  |  |  | Y |  |  | Proposed
46 | Khawaran,Shagy | Khogyani | DAI (AINP) | Compacted Gravel | ? |  |  |  |  | Y |  |  | WIP
47 | Ziarat Kaly | Hesarak | DAI (AINP) | Compacted Gravel | ? | 34.3118 | 69.7641 | 34.3344 | 69.716 | Y |  |  | WIP
48 | Miagan | Khogyani | DAI (AINP) | Compacted Gravel | ? | 34.2505 | 70.1824 | 34.2387 | 70.1544 | Y |  |  | WIP
49 | Tangi Miagan | Khogyani | DAI (AINP) | Compacted Gravel | ? |  |  |  |  | Y |  |  | WIP
50 | KOT VALLEY | Kot | DAI (AINP) | Compacted Gravel | ? | 34.2169 | 70.6633 | 34.1133 | 70.5411 | Y |  |  | Completed
51 | Sada,lal pur | Lal Pur | DAI (AINP) | Compacted Gravel | ? | 34.2505 | 71.0074 | 34.2536 | 71.0028 | Y |  |  | WIP
52 | Basawal,hazar na | Mohmand Dra | DAI (AINP) | Compacted Gravel | ? | 34.2505 | 70.8574 | 34.2536 | 70.8528 | Y |  |  | WIP
53 | Kodi kheal | Sherzad | DAI (AINP) | Compacted Gravel | ? | 34.243 | 69.9777 | 34.2435 | 69.978 | Y |  |  | WIP
54 | Hasham kheal | Sherzad | DAI (AINP) | Compacted Gravel | ? | 34.25 | 69.9968 | 34.2558 | 70.0112 | Y |  |  | WIP
55 | Mama kheal,Marke | Sherzad | DAI (AINP) | Compacted Gravel | ? | 34.247 | 69.995 | 34.218 | 70.029 | Y |  |  | WIP
56 | Bar Banga shear | Surkh Rod | DAI (AINP) | Compacted Gravel | ? | 34.3985 | 70.1016 | 34.4146 | 70.1055 | Y |  |  | WIP
57 | TORGHAR TATANG | Surkh Rod | DAI (AINP) | Compacted Gravel | ? | 34.3725 | 70.0859 | 34.3762 | 69.9239 | Y |  |  | WIP
58 | Jalalabad HWY1 Bypass | Jalalabad/Surkh Rod | DoPW | Paved | [5 empty] | Y |  |  | WIP
59 | Bawli to 134 Turnoff | Surkh Rod | NEEP/DoPW | Compacted Gravel | 5 |  |  |  |  | N |  |  | Proposed |  | NEEP or ALP?
60 | 135/134 Turnoff to Sherzad Turnoff | Khogyani/Sherzad | CERP | Compacted Gravel | 21.9 | 34.3499 | 70.1935 | 34.2844 | 70.0278 | Y | 2006-02-01 | 2006-07-01 | WIP
61 | Sherzad Bridge #1 | Sherzad | USAID (QIP) |  | 0.2 | 34.2811 | 70.0474 |  |  | Y |  |  | Proposed
62 | Sherzad Bridge #2 | Sherzad | CERP |  | 0.2 | 34.2844 | 70.0278 |  |  | N |  |  | Proposed